## dailytasklist
DAILY TASKS
| TASKS | STATUS | DUE DATE
2026-02-02 | Whisper OPENAI library study | ✅ Complete | 2026-02-10
| Whisper OPENAI library RUN on Urdu Audio | ✅ Complete | 2026-02-10
| Documentation of Working of Voice-Changer by w-okada github | 🏃 In progress | 2026-02-10
2026-02-03 | Brochure making AISIPS, EchoAIBot, Speech Texter | ✅ Complete | 2026-02-03
| Code Study - w-okada/Voice-Changer | 🏃 In progress | 2026-02-10
| Documentation of Working of Voice-Changer by w-okada github | 🏃 In progress | 2026-02-10
2026-02-04 | Code Study - w-okada/Voice-Changer | 🏃 In progress | 2026-02-10
| Documentation of Working of Voice-Changer by w-okada github | 🏃 In progress | 2026-02-10
2026-02-06 | Code Study - w-okada/Voice-Changer | 🏃 In progress | 2026-02-10
| Documentation of Working of Voice-Changer by w-okada github | 🏃 In progress | 2026-02-10
2026-02-09 | Code Study - w-okada/Voice-Changer | ✅ Complete | 2026-02-10
| Documentation of Working of Voice-Changer by w-okada github | ✅ Complete | 2026-02-10
| Notebook for Transcription - Different cases (Whisper, PreProcess+Whisper, Whisper+PostProcess, PreProcess+Whisper+PostProcess) | 🏃 In progress | 2026-02-13
2026-02-10 | Github updates | ✅ Complete | 2026-02-13
| Notebook for Transcription - Different cases (Whisper, PreProcess+Whisper, Whisper+PostProcess, PreProcess+Whisper+PostProcess) | ✅ Complete | 2026-02-13
2026-02-11 | Paper Changes "FaceMap" | ✅ Complete | -
| Voice-Changer --> Shift to offline (no cache kept) | 🏃 In progress | -
| Voice-Changer --> Change the Frontend | 🏃 In progress | -
2026-02-12 | Voice-Changer --> Shift to offline (no cache kept) --> Requirement check | ✅ Complete | -
| Voice-Changer --> Shift to offline (no cache kept) | 🏃 In progress | -
| Voice-Changer --> Change the Frontend | 🏃 In progress | -
2026-02-13 | Voice-Changer --> Change the Frontend --> divide in sections (header left right) | 🏃 In progress | -
| Journal Search for 'FaceMap' Paper | ✅ Complete | -
| Voice-Changer --> Shift to offline (no cache kept) | 🏃 In progress | -
2026-02-16 | OCR in Images (with different Python libraries and models) | ✅ Complete | -
| Object Detection | 🏃 In progress | -
| ResourceSpace and Dalet Comparison with DAMS | ✅ Complete | -
2026-02-17 | Object Detection Model Search and Testing (YOLO26, YOLOv8, YOLO12) | ✅ Complete | -
| Voice-Changer --> Shift to offline (no cache kept) | ❌ On hold | -
| Voice-Changer --> Change the Frontend | ❌ On hold | -
2026-02-18 | Object Detection Model Search and Testing (YOLO11, YOLOv8-world, YOLO12) | ✅ Complete | -
2026-02-19 | Object Detection Model Search and Testing (PP-YOLOE+) - Failed | ✅ Complete | -
2026-02-20 | Voice-Changer --> Shift to offline (no cache kept) | ✅ Complete | -
| Voice-Changer --> Change the Frontend --> Responsive WEB | ✅ Complete | -
2026-02-23 | Study ASR Urdu Models | ✅ Complete | -
| ASR models on HuggingFace (Search) | ✅ Complete | -
| ASR Datasets for Urdu Transcription | ✅ Complete | -
2026-02-24 | Study Finetuning Whisper Large V3 Model with LoRA and Audio Degradation | ✅ Complete | -
| Testing Whisper large v3 and Whisper large v3 tubo of OpenAI and Kingabzpro for URDU (also Asr_urdu model on HuggingFace) | ✅ Complete | -
| Finetuning Kingabzpro Whisper Large V3 Model with LoRA and Audio Degradation (Implementation) with LR=5e-5 | ✅ Complete | -
2026-02-25 | Finetuning Kingabzpro Whisper Large V3 Model with LoRA and Audio Degradation (Implementation) with LR=1e-5 | ✅ Complete | -
| Finetuning Kingabzpro Whisper Large V3 Model with LoRA and without Audio Degradation (Implementation) with LR=1e-5 | ✅ Complete | -
2026-02-26 | Finetuning OpenAI Whisper Large V3 Model with LoRA and Audio Degradation (Implementation) with LR=1e-5 | ✅ Complete | -
| Finetuning OpenAI Whisper Large V3 Model with LoRA and without Audio Degradation (Implementation) with LR=1e-5 | ✅ Complete | -
2026-02-27 | Testing Finetuning Kingabzpro Whisper Large V3 Model with LoRA and Audio Degradation (Implementation) with LR=5e-5 | ✅ Complete | -
| Testing Finetuning Kingabzpro Whisper Large V3 Model with LoRA and Audio Degradation (Implementation) with LR=1e-5 | ✅ Complete | -
| Testing Finetuning Kingabzpro Whisper Large V3 Model with LoRA and without Audio Degradation (Implementation) with LR=1e-5 | ✅ Complete | -
| Testing Finetuning OpenAI Whisper Large V3 Model with LoRA and Audio Degradation (Implementation) with LR=1e-5 | ✅ Complete | -
| Testing Finetuning OpenAI Whisper Large V3 Model with LoRA and without Audio Degradation (Implementation) with LR=1e-5 | ✅ Complete | -
2026-03-02 | Tested TurboScribe and ElevenLabs for Urdu Transcription | ✅ Complete | -
| Results Compilation for all testings | ✅ Complete | -
2026-03-03 | Observing the changes in audio transcription with respect to base | ✅ Complete | -
| Studying LLM-based Urdu transcription enhancement | ✅ Complete | -
2026-03-04 | The Alif model is used for Prompt-based spelling corrections and punctuations in output | ✅ Complete | -
| Result comparisons | ✅ Complete | -
2026-03-05 | Prompt enhancement for better outputs | 🏃 In progress | -
| Testing on different audios | ✅ Complete | -
2026-03-06 | Prompt enhancement (instead of Urdu, now English prompt) | ✅ Complete | -
| Testing on different audios | ✅ Complete | -
2026-03-09 | Result Compilation and comparisons | ✅ Complete | -
| Documenting Results | ✅ Complete | -

## Status
Status
⚠️Not started
🏃 In progress
✅ Complete
❌ On hold

## Models
Models/Frameworks | Path | Line # | Code | Column1
FastAPI for image inference | machine-learning/immich_ml/main.py | 165 | @app.post("/predict", dependencies=[Depends(update_state)])
Executes Predictions | machine-learning/immich_ml/main.py | 181 | async def run_inference(payload: Image ¦ str, entries: InferenceEntries) -> InferenceResponse:
Server Shutdown - no more BG tasks | machine-learning/immich_ml/main.py | 245 | async def idle_shutdown_task() -> None:
RetinaFace Model Load | machine-learning/immich_ml/main.py | 92-97 | if preload.facial_recognition.detection is not None: await load_models(preload.facial_recognition.detection, ModelType.DETECTION, ModelTask.FACIAL_RECOGNITION, )
ArcFaceONNX model load | machine-learning/immich_ml/main.py | 99-104 | if preload.facial_recognition.recognition is not None: await load_models( preload.facial_recognition.recognition, ModelType.RECOGNITION, ModelTask.FACIAL_RECOGNITION, )
RetinaFace | machine-learning/immich_ml/models/facial_recognition/detection.py | 4 | from insightface.model_zoo import RetinaFace
Input Decoding | machine-learning/immich_ml/models/facial_recognition/detection.py | 28 | inputs = decode_cv2(inputs)
Detection Threshold - minscore | machine-learning/immich_ml/models/facial_recognition/detection.py | 16, 17 | min_score: float = 0.7,
RetinaFace Model Load | machine-learning/immich_ml/models/facial_recognition/detection.py | 22, 23 | self.model = RetinaFace(session=session) self.model.prepare(ctx_id=0, det_thresh=self.min_score, input_size=(640, 640))
ArcFaceONNX | machine-learning/immich_ml/models/facial_recognition/recognition.py | 7 | from insightface.model_zoo import ArcFaceONNX
Image crop and affine transformations | machine-learning/immich_ml/models/facial_recognition/recognition.py | 8 | from insightface.utils.face_align import norm_crop | def norm_crop(img, landmark, image_size=112, mode='arcface'): M = estimate_norm(landmark, image_size, mode) warped = cv2.warpAffine(img, M, (image_size, image_size), borderValue=0.0) return warped
Embedding Normalization | machine-learning/immich_ml/models/facial_recognition/recognition.py | 15 | from immich_ml.models.transforms import decode_cv2, serialize_np_array
ArcFaceONNX model load | machine-learning/immich_ml/models/facial_recognition/recognition.py | 41 | self.model = ArcFaceONNX(self.model_path_for_format(ModelFormat.ONNX).as_posix(), session=session,)
Image crop | machine-learning/immich_ml/models/facial_recognition/recognition.py | 77 | return [norm_crop(image, landmark) for landmark in faces["landmarks"]]
Crop Image and Embeddings size | machine-learning/immich_ml/sessions/rknn/__init__.py | 38 | "recognition": {"input": {"norm_tensor:0": (1, 3, 112, 112)}, "output": {"norm_tensor:1": (1, 512)}},

## Server
Server
The Immich backend is divided into several services, which are run as individual docker containers.
1. immich-server - Handle and respond to REST API requests, execute background jobs (thumbnail generation, metadata extraction, transcoding, etc.)
2. immich-machine-learning - Execute machine learning models
3. postgres - Persistent data storage
4. redis- Queue management for background jobs